## Gantt of Gantts
|  |  | Monday | [6 empty] | Tuesday | [6 empty] | Wednesday | [6 empty] | Thursday | [6 empty] | Friday | [6 empty] | Monday | [6 empty] | Tuesday | [6 empty] | Total hours
| Who | % complete | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Creating website for 'Lofthus frukt og saft' |  | 0%
Administration and meetings |  | 0%
Start-up meeting with Lofthus |  | 0% | Monday 1: 5; Monday 2: 5; Monday 3: 5; Monday 4: 5 | 20
Final meeting, handing over website |  | 0% | Monday 7: 5; Tuesday 1: 5 | 10
Design the layout for the website |  | 0%
Design the global layout |  | 0% | Monday 5: 5; Monday 6: 5; Monday 7: 5; Tuesday 1: 5; Tuesday 2: 5; Tuesday 3: 5 | 30
Create/revise logo, brands and identity elements |  | 0% | Tuesday 4: 3; Tuesday 5: 3; Tuesday 6: 3; Tuesday 7: 3; Wednesday 1: 3; Wednesday 2: 3 | 18
Design colors and fonts, create design mock-up |  | 0% | [49 empty] | 5 | bar: Wednesday 3 to Wednesday 7
Meeting with Lofthus, present mock-up, get feedback |  | 0% | [49 empty] | 3 | bar: Thursday 2 to Thursday 4
Create and code the site |  | 0%
Research requirements for the website |  | 0% | Tuesday 4: 2; Tuesday 5: 2; Tuesday 6: 2; Tuesday 7: 2; Wednesday 1: 2; Wednesday 2: 2 | 12
Create code for global layout |  | 0% | Wednesday 3: 2; Wednesday 4: 2; Wednesday 5: 2; Wednesday 6: 2; Wednesday 7: 2; Thursday 1: 2 | 12
Create code for forms (order and contact) |  | 0% | Thursday 2: 2; Thursday 3: 2; Thursday 4: 2 | 6
Combine code and content, make adjustments |  | 0% | Thursday 5: 5; Thursday 6: 5; Thursday 7: 5; Friday 1: 5; Friday 2: 5; Friday 3: 5 | 30
Write content and find suitable photos |  | 0%
Find suitable photos and illustrations |  | 0% | [49 empty] | 5 | bar: Wednesday 3 to Wednesday 7
Create text for product pages and production info |  | 0% | [49 empty] | 5 | bar: Wednesday 3 to Wednesday 7
Testing and finalization |  | 0%
Test website, with Lofthus and externals |  | 0% | Friday 4: 2; Friday 5: 2; Friday 6: 2; Friday 7: 2; Monday 1: 2; Monday 2: 2; Monday 3: 2 | 14
Make last adjustments |  | 0% | Monday 4: 2; Monday 5: 2; Monday 6: 2 | 6
|  | Workload | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 176

## Admin Gantt
|  |  | Monday | [6 empty] | Tuesday | [6 empty] | Wednesday | [6 empty] | Thursday | [6 empty] | Friday | [6 empty] | Monday | [6 empty] | Tuesday
| Who | % complete | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Administration and meetings |  | 0%
Start-up meeting with Lofthus |  | 0%
Start-up meeting with Lofthus | Me | 0% | Monday 1: 5; Monday 2: 5; Monday 3: 5; Monday 4: 5
FED
DES
PHO
WRI
Final meeting, handing over website |  | 0%
Final meeting, handing over website | Me | 0% | Tuesday 1: 5; Tuesday 2: 5
FED
DES
PHO
WRI

## Design Gantt
|  |  | Monday | [6 empty] | Tuesday | [6 empty] | Wednesday | [6 empty] | Thursday | [6 empty] | Friday | [6 empty] | Monday | [6 empty] | Tuesday
| Who | % complete | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Design the layout for the website |  | 0%
Design the global layout |  | 0%
Design the global layout | Me | 0% | Monday 5: 5; Monday 6: 5; Monday 7: 5; Tuesday 1: 5; Tuesday 2: 5; Tuesday 3: 5
FED
DES
PHO
WRI
Create/revise logo, brands and identity elements |  | 0%
Create/revise logo, brands and identity elements | DES | 0% | Tuesday 4: 3; Tuesday 5: 3; Tuesday 6: 3; Tuesday 7: 3; Wednesday 1: 3; Wednesday 2: 3
PHO
WRI
Design colors and fonts, create design mock-up |  | 0%
Design colors and fonts, create design mock-up | DES | 0% | bar: Wednesday 3 to Wednesday 7
Meeting with Lofthus, present mock-up, get feedback |  | 0%
Meeting with Lofthus, present mock-up, get feedback | DES | 0% | bar: Thursday 2 to Thursday 4

## Code production Gantt
|  |  | Monday | [6 empty] | Tuesday | [6 empty] | Wednesday | [6 empty] | Thursday | [6 empty] | Friday | [6 empty] | Monday | [6 empty] | Tuesday
| Who | % complete | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Create and code the site |  | 0%
Research requirements for the website |  | 0%
Research requirements for the website | Me | 0% | Tuesday 4: 2; Tuesday 5: 2; Tuesday 6: 2; Tuesday 7: 2; Wednesday 1: 2; Wednesday 2: 2
FED
Create code for global layout |  | 0%
Create code for global layout | Me | 0% | Wednesday 3: 2; Wednesday 4: 2; Wednesday 5: 2; Wednesday 6: 2; Wednesday 7: 2; Thursday 1: 2
FED
Create code for forms (order and contact) |  | 0%
Create code for forms (order and contact) | Me | 0% | Thursday 2: 2; Thursday 3: 2; Thursday 4: 2
FED
Combine code and content, make adjustments |  | 0%
Combine code and content, make adjustments | Me | 0% | Thursday 5: 5; Thursday 6: 5; Thursday 7: 5; Friday 1: 5; Friday 2: 5; Friday 3: 5
FED
DES
PHO
WRI

## Content Gantt
|  |  | Monday | [6 empty] | Tuesday | [6 empty] | Wednesday | [6 empty] | Thursday | [6 empty] | Friday | [6 empty] | Monday | [6 empty] | Tuesday
| Who | % complete | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Write content and find suitable photos |  | 0%
Find suitable photos and illustrations |  | 0%
Find suitable photos and illustrations | PHO | 0% | bar: Wednesday 3 to Wednesday 7
Create text for product pages and production info |  | 0%
Create text for product pages and production info | WRI | 0% | bar: Wednesday 3 to Wednesday 7

## Testing Gantt
|  |  | Monday | [6 empty] | Tuesday | [6 empty] | Wednesday | [6 empty] | Thursday | [6 empty] | Friday | [6 empty] | Monday | [6 empty] | Tuesday
| Who | % complete | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Testing and finalization |  | 0%
Test website, with Lofthus and externals |  | 0%
Test website, with Lofthus and externals | Me | 0% | Friday 4: 2; Friday 5: 2; Friday 6: 2; Friday 7: 2; Monday 1: 2; Monday 2: 2; Monday 3: 2
DES
Make last adjustments |  | 0%
Make last adjustments | Me | 0% | Monday 4: 2; Monday 5: 2; Monday 6: 2
DES